{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":14,"n_cols":6,"rows_kept":14,"merged":[[0,0,0,5],[11,0,11,5],[12,1,12,4],[13,1,13,4]],"flags":["formulas_cached_only"]}
["建章立制工作计划推进表"]
["序号","工作项目","具体要求","完成时间","责任人","备注"]
[1,"将本单位岗位职责、规章制度的详细目录及联络人名单上交建章立制领导小组办公室(郭志戎)","各单位要按照郑铁学院党[2007]13号文件中规定的各单位主要职责来制订岗位职责和规章制度，2007年3月之前拟订和下发的所有岗位职责、规章制度及文件都要重新修订。尽量详尽，避免遗漏。","5月18日17：30前","各单位负责人"]
[2,"给各单位反馈意见","“建制办”开会讨论研究，给各单位提出修改意见。","5月21日17：30前","建制办"]
[3,"组织本单位人员讨论和学习，制订出岗位职责、规章制度的初稿并上报主管院领导审定","一定要参照和借鉴做得比较好的兄弟院校的经验，结合学院实际，岗位职责、规章制度的制订规格和完成质量要高。必要时要主动与学院其他单位协商，共同研究制订，不能出现“三不管”问题。","5月25日17：30前","各单位负责人"]
[4,"将领导审定后的本单位岗位职责、规章制度的初稿上交建章立制领导小组办公室(郭志戎)","文字稿必须由主管院领导签字。","5月30日17：30前","各单位负责人"]
[5,"汇集、整理各单位岗位职责、规章制度的初稿","“建制办”开会讨论研究，在参照兄弟院校成功经验，结合学院实际的基础上提出修改意见。","5月31日17：30前","建制办"]
[6,"上报学院领导审定",null,"6月3日 17：30前","建制办"]
[7,"给各单位反馈意见","将学院领导审定后的修改意见在反馈意见中注明。督促各单位尽快修改。","6月8日 17：30前","建制办"]
[8,"将重新修订后的本部门岗位职责、规章制度的最后定稿上交建章立制领导小组办公室(郭志戎)","按照办公室的统一要求、统一格式上报，具体格式另发。","6月15日17：30前","各单位负责人"]
[9,"上报党委会研究"]
["说明：1、各单位上报的目录和初稿要求统一使用WORD文档编辑，同时上交文字稿和电子稿。"]
[null,"2、各单位要严格按照推进表中要求的完成时间上报材料，不得延误。"]
[null,"3、建制办联系人：郭志戎，联系电话：6231（校电）、13503457201（手机）"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}